TERMS OF REFERENCE (TOR)

on

The Implementation Activities for Training Group II and III Companies under

# NIGERIA HCFC PHASE-OUT MANAGEMENT PLAN STAGE III 190173

- ORGANIZATIONAL BACKGROUND

The United Nations Industrial Development Organization (UNIDO) is the specialized agency of the United Nations that promotes industrial development for poverty reduction, inclusive globalization and environmental sustainability.  The mission of UNIDO, as described in the Lima Declaration adopted at the fifteenth session of the UNIDO General Conference in 2013 as well as the Abu Dhabi Declaration adopted at the eighteenth session of UNIDO General Conference in 2019, is to promote and accelerate inclusive and sustainable industrial development (ISID) in Member States. The relevance of ISID as an integrated approach to all three pillars of sustainable development is recognized by the 2030 Agenda for Sustainable Development and the related Sustainable Development Goals (SDGs), which will frame United Nations and country efforts towards sustainable development. UNIDO’s mandate is fully recognized in SDG-9, which calls to “Build resilient infrastructure, promote inclusive and sustainable industrialization and foster innovation”. The relevance of ISID, however, applies in greater or lesser extent to all SDGs. Accordingly, the Organization’s programmatic focus is structured in four strategic priorities: Creating shared prosperity; Advancing economic competitiveness; Safeguarding the environment; and Strengthening knowledge and institutions.

Each of these programmatic fields of activity contains a number of individual programmes, which are implemented in a holistic manner to achieve effective outcomes and impacts through UNIDO’s four enabling functions: (i) technical cooperation; (ii) analytical and research functions and policy advisory services; (iii) normative functions and standards and quality-related activities; and (iv) convening and partnerships for knowledge transfer, networking and industrial cooperation. Such core functions are carried out in Departments/Offices in its Headquarters, Regional Offices and Hubs and Country Offices.

The present task is within Montreal Protocol Unit (TCS/MPD) and the incumbent reports to the project manager in the unit.  The MPD is responsible for planning, developing and implementing activities in Member States to facilitate compliance with the Montreal Protocol and, in particular, it’s Kigali Amendment and to support countries to achieve their determined contributions to reduce emissions of greenhouse gases under the Paris Agreement. Making use of the capacity building and policy support, the services of the Unit foster transformation in manufacturing concerning technologies used in the refrigeration, air conditioning and insulation with the effect of a reduction and change in working fluids and chemicals and ultimately a reduction of total greenhouse gas emissions.

PROJECT CONTEXT

The HPMP for Nigeria, approved at the 62nd meeting of the Executive Committee, will result in the complete phase-out of HCFCs in Nigeria by 1st January 2040 in line with the obligation taken by the Government of Nigeria under the Montreal Protocol on Substances that Deplete the Ozone Layer. This is based on the combination of interrelated institutional and regulatory measures and investment activities including conversion of production facilities and strengthening of national capacities for local manufacture of hydrocarbon-based alternative refrigerants. UNDP is the lead agency for the implementation of this plan, UNIDO being the cooperating agency. Nigeria obtained financial support from the Multilateral Fund for the first stage, which resulted in the country attaining its 10% phase-out target of the baseline level by 2015. Nigeria also obtained at the 81st Executive Committee Meeting in June 2018 approval for its Second Stage of the HPMP, for a phase-out of 51.35% by 2023. For Stage II, UNDP was the coordinating agency, and both UNIDO and the Government of Italy are cooperating agencies.

After the ExCom Decision 81/40(c) noted that “approval of stage II of the HPMP did not preclude Nigeria from submitting, the 91st ExCom approved the HPMP Stage III.

Phase-out of HCFC-22 in the commercial refrigeration manufacturing sector

In the Nigeria market, there are already equipment using HC refrigerants on sale. The market and customers have gradually accepted such equipment and have certain application foundation and experience.

For the refrigerator, freezer, ice maker and RAC sector, the charging amounts of these refrigeration equipment are relatively small, and the overall design does not need after-sales installation (except RAC), so the risk of leakage is low. As an environmentally friendly high-performance refrigerant, HC can be used in small charges. At the same time, the compressor and other main parts are sufficiently supplied with many varieties, which can be applied to different refrigeration systems. The survey conducted in 2019 renewed the country’s portfolio of small and medium manufacturing companies in the field of commercial refrigeration. For eligible companies, the total HCFC-22 consumption in this sector is 232.29 MT (12.78 ODP tonnes) in 2019. Among them, 1 company consume more than 6 MT, 13 companies in the range of 3 to 6 MT, 53 companies less than 3 MT, and 115 companies less than 1MT.

UNIDO’s survey of HCFC consumption in the RAC manufacturing sector conducted in 2019 showed that out of 259 companies surveyed, only 183 companies in the commercial refrigeration manufacturing sector and 2 companies in air-conditioning manufacturing sector were found eligible to receive MLF support to phase out HCFC-22. Of the 185 eligible companies, only two produce air conditioning equipment, while other companies produce ice block making machines for walk-in refrigerators/freezers or install the walk-in refrigerators/freezers.

With the MLF Secretariat’s encouragement during its recent review of energy efficiency projects, it is convincing that R290 (not R32) technologies should be fully promoted in the commercial refrigeration sector. This choice has been supported by the fact that Sanden Intercool in Nigeria has fully converted its manufacturing line to R290. In April 2024, a training on the safe handling of R290 was conducted for 13 companies of group I in Lagos and Ibadan respectively. The R290 training mainly targeted commercial refrigeration manufacturers and assemblers. They were engaged in assembling, installing, and maintaining various types of refrigeration and air-conditioning equipment including cold rooms, ice making machines, central and residential AC, etc.

Kigali Implementation Plan (KIP) in Nigeria

Nigeria ratified the Kigali Amendment in 2018. The enabling activities funded by the Multilateral Fund with support from UNEP, assisted Nigeria in creating awareness of HFC phase-down, and supported the amendment of the National Environmental (Ozone Layer Protection) regulations. However, it was only in 2022, after the adoption of the amendment of the ODS regulation, that Nigeria started the implementation of the licensing system for HFCs. Quota allocations will be implemented fully in 2025 with the implementation of the KIP.

HCFC consumption of Nigeria in 2023 reached 1,844MT. Implementing agencies including UNDP and UNIDO are supporting Nigeria on the implementation of stage II and Stage III HPMP in parallel, Stage IV of the HPMP will be developed to completely phase out HCFCs by 2030. It is expected that HPMP and KIP could be designed and implemented in a complementary manner to strengthen the infrastructure and capacity of the country for a sustainable HCFC phase-out and HFC phasing down for Nigeria.

Table 3.1: Summary of Eligible Companies by HCFC-22 Consumption in the commercial refrigeration sector

| Enterprise Category | HCFC-22 Consumption (MT) | Number of Companies | Total HCFC-22 Consumption |  |
| --- | --- | --- | --- | --- |
|  |  |  | (MT) | (ODP tonnes) |
| Individual conversion | HCFC-22 > 6 MT | 1 | 10.07 | 0.55 |
| Group conversion 1 | 3 < HCFC-22 ≤ 6 MT | 13 | 57.2 | 3.15 |
| Group conversion 2 | 1 < HCFC-22 ≤ 3 MT | 53 | 120.5 | 6.63 |
| Group Conversion 3 | HCFC-22<1MT | 115 | 44.52 | 2.45 |
| Total |  | 182 | 232.29 | 12.78 |

In order to promote and accelerate the phase-down of HCFC and shift towards low GWP alternatives, the eligible companies are divided into three groups in designing the technical assistance in Stage III:

- Individual Conversion: Solutions for the enterprises will be highly customized and HC will be selected wherever possible. Efforts would be made to understand each company’s situation and capacity, and tailor-made solutions would be proposed and implemented;

- Group Conversion 1: The enterprises could choose from ready-made equipment components needed for handling HC-290 within the project budget. The companies could choose to incorporate additional solutions with additional payments; and

- Group Conversion 2: The enterprises would be provided with technical assistance and training.

- Group Conversion 3: The enterprises would be provided with technical assistance and training.

See list of Group II enterprises to be trained below:

| S/n | Company | Location | Geo-political zone |
| --- | --- | --- | --- |
| 1 | Perabeam Limited | Lagos State | South West |
| 2 | Baosam Concepts | Ibadan | South West |
| 3 | A O A Technical Company | Oyo/Ibadan | South West |
| 4 | Chris Sunny Refrigeration | Kwara/Ilorin | South West |
| 5 | Edencool Technical Works | Oyo/Ibadan | South West |
| 6 | Ade Tech | Oyo/Iseyin | South West |
| 7 | Awosco Cooling Works | Oyo/Ibadan | South West |
| 8 | Adekola Adewale Tech Engineering | Oyo/Ibadan | South West |
| 9 | Odunyemi Commercial Enterprises | Oyo/Ogbomoso | South West |
| 10 | Folab Technical Works | Oyo/Ibadan | South West |
| 11 | Souna Ventures | Kogi/Lokoja | North Central |
| 12 | ABIODUN TECHNICAL SERVICE | OGUN STATE | South West |
| 13 | Das Bam and Company Ltd | Lagos/Lagos | South west |
| 14 | MICHAEL FAST COOL NIG. | BENIN | South South |
| 15 | Gab Technical Works | Kano/Kano | North West |
| 16 | OBI ELECTRICAL ENGINEERING | ONITSHA | South East |
| 17 | CHARLES ORANEBO INVESTMEENT NIG. | OBOSI/Anambra | South East |
| 18 | VIC - MON TECHNICAL | Abuja/Abuja | North Central |
| 19 | FELIX COOLING TECHNICAL | BENIN | South South |
| 20 | Amusat Oladoke Enterprises | Oyo/Saki | South West |
| 21 | Mazadu Technical Enterprises | Kano/Kano | North West |
| 22 | S. ABBEY NIGERIA COMPANY ENT. | ABEOKUTA | South West |
| 23 | Supreme Refrigeration Works | Kwara/ Ilorin | South West |
| 24 | Femtek Nig Enterprises | Oyo/Iseyin | South West |
| 25 | TAJUDEEN ALIMI CASH AND CARRY TECHNICAL SERVICES | Kano/Kano | North West |
| 26 | Aliiko Refrigeration Services | Kwara/Ilorin | North Central |
| 27 | A K Faithful Technical Industries | Oyo/Ibadan | South West |
| 28 | Easy Solution Technical Works | Kwara/Ilorin | North Central |
| 29 | JOE TECHNICAL & COMPANY | ABUJA | North Central |
| 30 | Soltech Refrigeratiuon Works (Nigeria) | Oyo/Ibadan | South West |
| 31 | Jide Tech Co. | Kano/Kano | North West |
| 32 | PHILIP COOL TECH. COMPANY | ABUJA | North Central |
| 33 | ADVANTAGE TECHNICAL SEERVICES | Abuja | North Central |
| 34 | AKAND-ALADE ALLIU TWINS TEC | Lagos/ Lagos | South West |
| 35 | Clem Makanjuola Nig Ent. | Lagos/Lagos | South west |
| 36 | Ubani Technical Services | Kano/Kano | North West |
| 37 | Evercurrent Technical Company | Kano/Kano | North West |
| 38 | DEVY TECHNICA SERVICES | ABUJA | North Central |
| 39 | Jubson Technical Company | Akure/ Ondo | South West |
| 40 | Abiodun Morakinyo Nig Enterprises | Oyo/Oyo | South West |
| 41 | Morakinyo De Cool Merchant Nig Company | Oyo/Oyo | South West |
| 42 | Mofol Cool | Oyo/Iseyin | South West |
| 43 | Fash Tech Consult | Oyo/Ibadan | South West |
| 44 | Sam Goodness Technical Enterprise | Oyo/Ibadan | South West |
| 45 | Missty Tee Tech Multiservice4s | Oyo/Ibadan | South West |
| 46 | Bencool Tech Int | Akure/Ondo | South West |
| 47 | A Honesty Tech/General Ent. | Kano/Kano | North West |
| 48 | MAKANOH TECH. NIG. | ABUJA | North Central |
| 49 | Dare Kilaso Ventures | Kano/Kano | North West |
| 50 | ASSURANCE TECH. ENG. WORK | ABUJA | North Central |
| 51 | Nino Technical Services | Abuja | North Central |
| 52 | AMUDA JAMIU AFOLABI JAMOTECH VENTURE | Lagos State | South West |
| 53 | Elharun Construction Company | Kaduna/Kaduna | North West |

See a list of all 115 Group III companies to be trained below:

| S/n | Company | Location | Geo-political zone | Type of business |
| --- | --- | --- | --- | --- |
| 1 | Sholl-Sammy Associate (ENGR) Works | Kano/Kano | Norh West | ICE MAKING MACHINE/ COLD ROOM |
| 2 | MARTINS TECHNICAL COMPANY | ABUJA | North Central | ICE MAKING MACHINE |
| 3 | AUSREAL TECHNICAL CO. | ABUJA | North Central | ICE MAKING MACHINE |
| 4 | Johnson Kay Services | Kwara/Ilorin | North Central | ICE MAKING MACHINE/ COLD ROOM |
| 5 | Koseru Technical Services | Kwara/Ilorin | North Central | ICE MAKING MACHINE/ COLD ROOM |
| 6 | Oyetech Nig | Kwara/Ilorin | North Central | ICE MAKING MACHINE/ COLD ROOM |
| 7 | R & A Place | Kwara/Ilorin | North Central | ICE MAKING MACHINE/ COLD ROOM |
| 8 | HOLY WATER TECHNICAL ENTERPRISE | ABUJA | North Central | ICE MAKING MACHINE/ WATER COOLING MACHINE |
| 9 | OKOTI TECHNICAL COMPANY LTD | ABUJA | North Central | ICE MAKING MACHINE |
| 10 | Flamin go Cooling (NIG) enterprise | Kogi/Ajaokuta | North Central | ICE MAKING MACHINE |
| 11 | MACHI TECH | ABUJA | North central | ICE MAKING MACHINE |
| 12 | JASMOD NIG ENTERPRISES | Abuja | North central | ICE MAKING MACHINE |
| 13 | J. J. Johnson Engineering Enterprises | Kogi/Lokoja | North central | ICE MAKING MACHINE/ COLD ROOM |
| 14 | FEMOO COOL NIGERIA LTD | Abuja | North Central | ICE MAKING MACHINE/ COOLER BOX |
| 15 | FRANCO ELECTRICAL WORK | Abuja | North Central | ICE MAKING MACHINE |
| 16 | BAABAGIDA IBRAHIM ELECTRICAL | Abuja | North Central | ICE MAKING MACHINE |
| 17 | THEERMOCOOL COOL WORLD ENTERPRISES | Abuja | North Central | ICE MAKING MACHINE |
| 18 | JOHNYCOOL TECH. VENTURE | Abuja | North Central | ICE MAKING MACHINE |
| 19 | JODAMAF TECH. NIG. LTD | Abuja | North central | ICE MAKING MACHINE |
| 20 | DANY BEST TECHNICAL VENTURE | ABUJA | North Central | ICE MAKING MACHINE |
| 21 | JOF-TECH TECHNICAL COMPANY | Abuja | North Central | ICE MAKING MACHINE |
| 22 | JOHN OSIKE FABRICATION WORK | Abuja | North Central | ICE MAKING MACHINE |
| 23 | DE-RAY AND CO TECH | Abuja | North Central | ICE MAKING MACHINE |
| 24 | ALIU COOLS TECH. CO | Abuja | North Central | ICE MAKING MACHINE |
| 25 | ELECTRO-DATERO NIGERIA LIMITED | Abuja | North central | ICE MAKING MACHINE |
| 26 | OLALEYE TECHNICAL LTD | Abuja | North Central | ICE MAKING MACHINE/ COLD ROOM/PURE WATER |
| 27 | SHONCOOL REFRIGERATINO AIR COND. ENTERPRISES | Abuja | North Central | ICE MAKING MACHINE /COLD ROOM/FRIDGE/ AIR CONDDITIONER |
| 28 | COOLCITY FRIDGE TECHNICAL COMPANY | Abuja | North central | ICE MAKING MACHINE/ OVEN/ LOCAL BAKERY |
| 29 | USARIK ENG. NIG LTD | Abuja | North Central | ICE MAKING MACHINE |
| 30 | AZEMOH & AZEMOH TECH SERVICE | Abuja | North Central | ICE MAKING MACHINE |
| 31 | ALBARKA WAVES CONCEPT LTD | ABUJA | North central | ICE MAKING MACHINE/ COLD ROOM |
| 32 | EZETHEC TECHNICAL SERVICES | Abuja | North Central | ICE MAKING MACHINE |
| 33 | Dens and Sons Nig Ent | Kogi/Lokoja | North Central | ICE MAKING MACHINE |
| 34 | FRIJIM ELECTRICAL ELECTRONIC | ABUJA | North central | ICE MAKING MACHINE /COLD ROOM |
| 35 | EMMANCO ANHERI ENT. | Abuja | North Central | ICE MAKING MACHINE |
| 36 | CHAN - THE COOL ENT. | Abuja | North Central | ICE MAKING MACHINE/ COLD ROOM |
| 37 | CHUKS COOL TECH. COMPANY | Abuja | North Central | ICE MAKING MACHINE |
| 38 | KAYBETH TECHNICAL | ABUJA | North Central | ICE MAKING MACHINE |
| 39 | DOECCOOL TECHNICAL | Abuja | North Central | ICE MAKING MACHINE |
| 40 | ISIAKU MUSA ELECTRICAL WORK | Abuja | North central | ICE MAKING MACHINE |
| 41 | FANEX SYSTEM NIG. | ABUJA | North central | ICE MAKING MACHINE |
| 42 | SOLOTECH ELECT. NIG. ENT. A/C & REF. | ABUJA | North central | ICE MAKING MACHINE |
| 43 | Ibrahim Muazu Tech Works | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 44 | United Tech Enterprises (Babington Technical Enterprises) | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 45 | Patrick Abu Technical Company | Kano/Kano | North West | ICE MAKING MACHINE |
| 46 | N U Engineering Tech | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 47 | Rivers Electrical & Mechanical Company | Kano/Kano | North West | ICE MAKING MACHINE |
| 48 | Hamadex Technical Services | Kano/Kano | North West | ICE MAKING MACHINE |
| 49 | Suleiman Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 50 | OC Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 51 | BESTMAN TECHNICAL WORKS | Abuja | North West | ICE MAKING MACHINE |
| 52 | Taoteco Technical Works | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 53 | Aray Home Air Conditioning Clinic | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 54 | God With Us Feel Engineered Works | Kaduna/Kaduna | North West | ICE MAKING MACHINE |
| 55 | Tunde Technical Services | Kano/Kano | North West | ICE MAKING MACHINE |
| 56 | Tadlok enterprises | Kano/Kano | North west | ICE MAKING MACHINE/ COLD ROOM |
| 57 | Champion Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 58 | Taiye Technical Works | Kano/Kano | North west | ICE MAKING MACHINE/ COLD ROOM |
| 59 | Abbey Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 60 | Tajudeen Abdulsalam Tech Works | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 61 | Sam Technical Refridgelant | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 62 | Amark Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 63 | Tunde Technical Works | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |
| 64 | Achyman Global Link Services | Kaduna/Kaduna | North West | ICE MAKING MACHINE/ COLD ROOM |
| 65 | ADAMS TECH. EMERGENCY | Abuja | Noth Central | ICE MAKING MACHINE |
| 66 | Olurotimi Olufowose NIG Ent | Oyo/Ibadan | South West | ICE MAKING MACHINE |
| 67 | IFECO CONSRUCTINO CO. NIG. | Obosi/Anambra | South East | ICE MAKING MACHINE/ ICE CREAM, BOTTLE WATER, DEEP FREEZER |
| 68 | N-NDU ELECTRICAL | Aba | South East | ICE MAKING MACHINE |
| 69 | PEE COOLING TECH. | Aba | South East | ICE MAKING MACHINE/ COLD ROOM |
| 70 | GODS OPINIO TECHNICAL NIG. | ONITSHA | South East | ICE MAKING MACHINE |
| 71 | E-PAL ENTERPRISES NIG LTD | Aba | South East | ICE MAKING MACHINE |
| 72 | UGOWE ENG. COMPANY | Benin | South South | ICE MAKING MACHINE/COLD ROOM/ BUILDING OF MINI COLD |
| 73 | GEOWHO ENINGEERING INTERNATIONAL COMPANY | Portharcourt | South South | ICE MAKING MACHINE/ CENTRAL UNIT, COLD STORE |
| 74 | CHRISTOLY NIG. ENTERPRISES | PORT HARCOURT | South south | ICE MAKING MACHINE |
| 75 | OGTECH ELBART LTD | PORT HARCOURT | South South | ICE MAKING MACHINE/ COLD ROOM |
| 76 | A. Z. MOMOH NIGERIA LTD | Port Harcourt | South south | INDUSTRIAL COLD ROOM, MARINE COLD ROOM, BOX TRUK COLD ROOM |
| 77 | BAYOSON TECHNICAL | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |
| 78 | OHAVIC VENTURES | PORT HARCOURT | South South | ICE MAKING MACHINE |
| 79 | SAROCOOL TECHNICAL SERVICES | PORT HARCOURT | South South | ICE MAKING MACHINE |
| 80 | NESCO TECHNICAL SERVICE CO. | PORT HARCOURT | South south | BOX TRUCK COLD ROOM, MARINE COLD ROOM, INDUSTRIAL COLD ROOM |
| 81 | AUSTIN LAZ & CO PLC | BENIN | South South | ICE MAKING MACHINE |
| 82 | DE HEROES REFRIGERANTINO CO. | PORT HARCOURT | south south | COLD ROOM/ INDUSTRIAL REFRIGERATION |
| 83 | ANGSONS ENTERPRISES | PORT HARCOURT | South south | ICE MAKING MACHINE/ COLD ROOM |
| 84 | COOLMAN TECH SERVICES | Akwa Ibom | South south | COLD ROOM |
| 85 | Pauli Brothers and Company | Enugu/Enugu | South East | ICE MAKING MACHINE |
| 86 | SamueL Technical Works | Oyo/Oyo | South West | ICE MAKING MACHINE |
| 87 | Jumascoi Technical Engineering Company | Oyo/Ibadan | South West | ICE MAKING MACHINE/ COLD ROOM |
| 88 | BEST JOHNNY TECHNICAL COMPANY | Abeokuta | South West | ICE MAKING MACHINE |
| 89 | AJAYI EZEKIEL | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |
| 90 | Castrol Joe Tech. | Akure/Ondo | South West | COLD ROOM |
| 91 | SIKFAT COMM. ENT. | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |
| 92 | ELECTRICAL ENG. CO. | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |
| 93 | OLALEKANCOOL SERVICES NIG. | Lagos | South West | ICE MAKING MACHINE |
| 94 | AJITECH TECHNIAL SERVICES | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |
| 95 | Oyegoke Electrical Works | Oyo/Ibadan | South West | ICE MAKING MACHINE/ CHILLERS, AIR CONDITIONERS |
| 96 | Nurudeen Adeojua Ice Block Making Machine | Oyo/Ibadan | South West | ICE MAKING MACHINE/ COLD ROOM |
| 97 | Orosun Nigeria Limited | Ogun/Ijebu Ode | South west | ICE MAKING MACHINE |
| 98 | OLU-ADE TECHNICAL SERVICES | ABEOKUTA OGUN STATE | South West | ICE MAKING MACHINE |
| 99 | Dansfocus Technical Company | Oyo/Ibadan | South West | ICE MAKING MACHINE |
| 100 | FAVOUR ONA VENTURE | ABEOKUTA OGUN STATE | South west | ICE MAKING MACHINE |
| 101 | Deekay and Sons Nigeria LTD | Lagos/Lagos | South West | Nexus refrigeration appliances and air conditioners |
| 102 | SUNNY OKEOWO NIGERIA ENTERPRISE | Lagos State | South west | ICE MAKING MACHINE |
| 103 | Moonlight Electrocooling Services | Oyo/Ibadan | South west | ICE MAKING MACHINE/ COLD ROOM |
| 104 | Adrosh Co Ltd | Lagos State | South West | ICE MAKING MACHINE |
| 105 | Hamzat Technical Services | Lagos/Lagos | South West | ICE MAKING MACHINE |
| 106 | Popson Technology Service Works | IBADAN | South west | ICE MAKING MACHINE |
| 107 | BIDBELL VENTURES | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |
| 108 | Polade | Lagos State | South West | ICE MAKING MACHINE/ COLD-ROOM PANES, SPRAY WORK |
| 109 | DEKOOLAR NIG LTD | Papalanto/Ogun State | South west | ICE MAKING MACHINE/ COLD ROOM/ FREEZER/ OVEN |
| 110 | Fakeye Corporate Enterprises | Oyo/Ibadan | South West | ICE MAKING MACHINE |
| 111 | AjibadeTech Work | Oyo/Ibadan | South West | ICE MAKING MACHINE |
| 112 | Samdeb (Nig) Enterprises | Ibadan/Oyo | South west | ICE MAKING MACHINE/ CHILLERS, AIR CONDITIONERS |
| 113 | OLATEECH | Lagos | South west | ICE MAKING MACHINE/ COLD ROOM |
| 114 | Coldcare Nigeria Ltd | Lagos State | South West | commercial, industrial and residential refrigeration |
| 115 | OSENI TECH. ENTERPRISE | OGUN STATE | South West | ICE MAKING MACHINE |

KIP companies

| S/n | Company | Location | Name of geo-political zone | Type of business |
| --- | --- | --- | --- | --- |
| 1 | Fouani Nig Ltd | Lagos | South West | Refrigerators, Freezers and Acs (LG, Hisense) |
| 2 | New Homes Distribution Africa Ltd | Lagos | South West | ACs and Frigdes (Midea and Scanfrost) |
| 3 | Cold Hubs Ltd | Lagos | South West | Cool rooms |
| 4 | Koolboks Nig. Ltd | Lagos | South West | Koolboks Freezers |
| 5 | SIM Nig. Ltd | Lagos | South West | Refrigerators/Freezers |
| 6 | JMG Ltd Abuja | Abuja | North Central | Fridges, Freezers and ACs ( TCL, AEON, Toshiba) |
| 7 | JNC Motors Ltd | Abuja | North Central | ACs (Gee) |
| 8 | Choice International Group (CIG) Motors Co. Ltd | Abuja | North Central | GAC Motors, JMC Motors and Wulling Motors |
| 9 | JAC Motors Ltd | Lagos | South West | JAC Motors |
| 10 | Innoson Vehicle Manufacturing co. ltd | Anamabra | South East | Innoson Motors |

- Purpose of the Term of Reference

The primary objective of the terms of reference is to guide on the training activities for the Nigerian commercial refrigeration enterprises on their conversion to R290 under the HPMP Stage III project. This contract is for the logistical organization of training for 53 companies of Group II, as well as for 115 companies of Group III and for 10 companies of KIP, which will be conducted in the government identified centers of excellence across the country.

The planning of the logistical organization of training sessions must be done in close coordination with the National Ozone Office (NOO) of Nigeria and two trainers, who will share the training materials and any other additional considerations.

After completion of these training sessions, a separate final training (one day) must be held. This session will host Group I, Group II, Group III and 15 KIP companies (in total 196 companies/ trainees) again and will summarize the most important lessons learned, as well as a demonstration of usage of a logbook.

Training Modules and Topics

Participants’ training module will be mostly focused on the areas mentioned below:

- Thermodynamics and refrigeration cycles

- H-P chart

- Types and physio-chemical properties of refrigerants HFCF, HFCs, HFOs, HC, CO2, NH3 and blends and safe handling of the flammable and toxic refrigerants and lubricants

- Type of commercial refrigeration and AC systems

- Electrical wiring basics and safety

- Vacuum and vacuum pumps including anti-explosion (ATEX) pumps

- Choice of appliances and systems

- Installation, servicing, maintenance, repair or decommissioning of the equipment

- Leak checks of the equipment

- Minimizing leaks

- Refrigerant identification

- Safe handling of cylinders (disposable and recovery cylinders)

- Contamination test kits

- Storage of used refrigerants

- Hermetic seals (blazing v.s. lockring, etc.)

- Good servicing practices

- Environmental impacts

- Energy efficiency of different refrigerants

- HCFC Phase-out Management Plan and Kigali Implementation Plan

- Key manufacturing process (pre-foaming, foaming, post-foaming, vacuuming, charging, leak check, electrical testing, etc.)

- Effective data and record keeping

The last day of trainings must be dedicated to the maintenance and proper cleaning of the devices and equipment. This means demonstrating to the trainees how to take care of the equipment in order to ensure a safe, sustainable and long usage of the equipment.

- Scope of work

Under the direct supervision of the UNIDO Project Manager and in close coordination with the National Ozone Office, the contractor shall implement the following tasks:

a. Secure identified training centres for the duration of training programme and support the successful execution of the training exercises

Under this task, the contractor will be responsible for:

- Organizing ten three-days training sessions in three training centres in three locations: Lagos, Kano and Port Harcourt;

- Developing a sex segregated list of trainers and trainees;

- Advising and guiding the training plans and methodology, for review by UNIDO and NOO;

- Developing training agenda, in close coordination with the UNIDO trainers, and sharing with UNIDO and NOO for review;

- In close coordination with NOO and UNIDO, identify suitable dates for all the trainings;

- Liaise with the identified training centres, and ensure all materials and equipment is there before the training

- In close coordination with the UNIDO trainers, administer pre and post-test questionnaires and submit to UNIDO;

- Print training materials and manuals for the dissemination to training participants. Developing general evaluation sheet of the training (to include venue, equipment, logistics, coordination etc), administer to trainee enterprises and submit to UNIDO;

- Submitting a detailed training report alongside a segregated list of participants and identifying areas of improvement to plan, direct, organize, and schedule for subsequent training programs.

- Coordinate all logistic and training actions

The contractor shall perform the following:

- Identify and provide suitable accommodation for all trainees; within the UNIDO Daily Sustenance Allowance (DSA)

- Book air/bus/train tickets or transportation for participants attending from other cities to the designated training location;

- Provide intra city transportation for transfers to and from the hotel and the training centre after each day’s training and for any other necessary destinations;

- Book hotels/any other suitable accommodation booking for all trainees;

- Pay the trainees Daily Sustenance Allowance (DSA) as appropriate and as agreed by UNIDO and NOO. The exact DSA amount should comply with UNIDO rules and the exact amount to be disseminated to trainees will be shared with a successful bidder.

- Media/visibility:

In consultation with UNIDO and NOO;

- Design and print UNIDO and NOO branded training materials and banners. UNIDO will share training materials in doc and pdf formats for further printing. Two banners must be designed and printed per location: two for Kano, two for Port Harcourt and two for Lagos. Additional two banners must be designed and printed for the final workshop in Lagos, where all companies would be invited. The contractor is to print hard copies of the training materials. The material should be in A4 size, 80 gsm (thickness 0.09 mm - 0.11 mm) and either spiral or thread bound. In total 178 trainees will attend the trainings, with a buffer in case of loss or damage, the contractor should print 200 hard copies.

- Design and bring UNIDO and NOO sets of branded souvenirs to the training center. One set of branded souvenirs should contain one jotter (A5, hardcover, paper thickness of 80 gsm (0.09mm - 0.11mm), one pen, one hat and one workshop bag.  In total 178 trainees will attend the trainings, with a buffer in case of loss or damage, the contractor must bring 200 sets of branded souvenirs.

- In close coordination with NOO and UNIDO trainers, a Certificate of Participation to be shared with trainees for NOO and UNIDO’s signature. The UNIDO template for Certificates will be provided by UNIDO.

- Bring 200 copies of a logbook for the final training. The logbook must have a paper density of 110 gsm (0.12 mm). This logbook must also be provided in digital form to UNIDO and NOO.

- Provide professional pictures from all training sessions through a verified and safe link and a copy in an external hard drive;

- Develop a media briefing and submit to UNIDO, not later than 3 working days after the trainings sessions in one location have been finished.  A final report is expected after the final training in Lagos.

- Procure new safety boots and reflective jackets for the purpose of the training (200 safety boots and 200 reflective jackets to be disseminated for the training participants);

- Provide media coverage for the training at the designated training locations e.g. TV, radio, prints, social media etc. Each training shall be reported in at 5 different media sources;

- Develop a communications video for each of the training locations and a joint video for all the Group 2 and Group 3 trainings. Two versions shall be submitted; an abridged version of not more than 3 minutes each and an original version.

- Others:

- Ensure that UNIDO’s name and brand is protected at all times;

- Organize the provision of water and coffee during the training session;

- Ensure safe storage at each training centre, UNIDO procured equipment/materials for enterprises and in the presence of UNIDO and NOO ensure distribution and presentation of equipment to trainee enterprises

- Location

Locations of Training

The trainings will be held for the 53 Group II enterprises and 115 Group III and 10 KIP companies at 3 designated Centres of Excellence as designed by the National Ozone Office (NOO) of Nigeria. The training will be held at Kano, Port Harcourt and Lagos.

| Sr. No. | Training Center | Location (City/State) | Equipment Available | Classroom Capacity |
| --- | --- | --- | --- | --- |
| 1. | Cool Plus Limited | Plot 23, Theophilus Oji Street, off Fola Osibo Road, Lekki Phase 1, Lagos State | Recovery Machines for R-22, Recovery tank, Refrigerant recovery cylinders (30lb), Vacuum pump, Vacuum gauge Brazing set, Pinch off tool, Electronic refrigerant scale, Normal Leak detector, service manifold, electronic gauges, electronic hoses and assesories, hoses with valves Service port coupler, set Core removal tool Piecing plier including valve Charging hose and cylinder connections Heating belt with thermostat, Thermometer, electronic Multimeter with clamp on amp mesurement Tools for tubing General tube cutters Capilary tube cutter Pinch off plier Flaring tool Tube bender Tube expander Brazing equipment and tips Igniter Consumebles, 1 set Safety equipment Safety Glasses Gloves Hydro Carbon Service Tools N2 flushing equipment HC Leak detector HC Charging equipment Venting hoses and asessories Refrigerant Identifier Portable recycling machine External filter kits Burn out filter assesories Test rack with instruments. | Each group will have three-day training Group II 27 trainees (1 per enterprise) Group III 42 trainees (1 per enterprise) + 10 trainees (1 per enterprise from KIP) |
| 2. | Government Technical College | No 1 State Road, Opposite Kano Line, Kano. Kano State | Recovery Machines for R-22, Recovery tank, Refrigerant recovery cylinders (30lb), Vacuum pump, Brazing set, Pinch off tool, Electronic refrigerant scale, Normal Leak detector, service manifold, gauges and assesories, hoses with valves, Service port coupler, set Core removal tool, Piecing plier including valve, Charging hose and cylinder connections, electronic Multimeter with clamp on amp measurement, General tube cutters, Pinch off plier, Flaring tool, Tube bender, Tube expander, Brazing equipment and tips, Igniter, Consumebles, 1 set, Safety equipment, Safety Glasses, Gloves Hydro Carbon Service Tools, N2 flushing equipment, HC Leak detector, HC Charging equipment, Venting hoses and asessories, Refrigerant Identifier Portable recycling machine, External filter kits, Test rack with instruments. | Three-days training session for: Group II 22 trainees (1 per enterprise) Group III 65 trainees (1 per enterprise) |
| 3. | Government Craft Development Center | Aba Road, by Garison Junction, GRA, Port Harcourt, Rivers State | Recovery Machines for R-22, Recovery tank, Refrigerant recovery cylinders (30lb), Vacuum pump, Brazing set, Pinch off tool, Electronic refrigerant scale, Normal Leak detector, service manifold, gauges and assesories, hoses with valves, Service port coupler, set Core removal tool, Piecing plier including valve, Charging hose and cylinder connections, electronic Multimeter with clamp on amp measurement, General tube cutters, Pinch off plier, Flaring tool, Tube bender, Tube expander, Brazing equipment and tips, Igniter, Consumebles, 1 set, Safety equipment, Safety Glasses, Gloves Hydro Carbon Service Tools, N2 flushing equipment, HC Leak detector, HC Charging equipment, Venting hoses and asessories, Refrigerant Identifier Portable recycling machine, External filter kits, Test rack with instruments. | Three-days training session for one group Group II 4 trainees (1 per enterprise) Group III 18 trainees (1 per enterprise) |

The 53 Group 2 enterprises will be divided across the three locations according to the geographical locations and their nearness to any of the designated training centres.

Enterprises for training at Kano designated centre

| S/n | Company | Name of contact person | Number of contact person | Email address of contact person | Geo-political zone | Type of business | Training session |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Souna Ventures | Chief olukoyade Olonishuwa | 08055615938 | sounaventuresnigltd@gmail.com | North Central | ICE MAKING MACHINE | Session #1 (one trainee per company) |
| 2 | Aliiko Refrigeration Services | Babatunde Ayinde Musa | 08030691076 |  | North Central | ICE MAKING MACHINE |  |
| 3 | Easy Solution Technical Works | Ibrahim Isiaka | 07030611668, 07034356211 |  | North Central | ICE MAKING MACHINE/ COLD ROOM |  |
| 4 | Joe Technical & Company | Joseph N. Nwaru | 08032883551, 07010666507 |  | North Central | ICE MAKING MACHINE |  |
| 5 | Philip Cool Tech. Company | Philip Thomas | 0-8036905053 |  | North Central | ICE MAKING MACHINE |  |
| 6 | Advantage Technical Services | Ugwoegbulem Addindu Hyacinth | 0-8033596398 | Okotidavid@yahoo.com | North Central | ICE MAKING MACHINE |  |
| 7 | Devy Technical Services | David Onoja | 0-8036127845 | jimohmakasa@gmail.com | North Central | ICE MAKING MACHINE |  |
| 8 | Makanoh Tech. Nig. | Mathew K.C. Onuoha | 0-8059467963 |  | North Central | ICE MAKING MACHINE |  |
| 9 | Assurance Tech. Eng. Work | Clement O. Ekunke | 0-8037052123/ 0-8075828735 | omomejifo@gmail.com | North Central | ICE MAKING MACHINE |  |
| 10 | Nino Technical Services | Austin Okhumhoya | 08037016238 08054678050 | austinokhumhoya@gmail.com | North Central | COLD ROOM |  |
| 11 | Gab Technical Works | Gabriel Okhari | '08039642468 | okharigabriel68@gmail.com | North West | COLD ROOM |  |
| 12 | Mazadu Technical Enterprises | Ado Mohammad | 08034556440 | adomuhmmad@gmail.com | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 13 | Tajudeen Alimi Cash and Cary Techical Services |  | 08137250027 | jsanni54@gmail.com | North West | ICE MAKING MACHINE |  |
| 14 | Jide Tech Co. | Jide Komolafe | 08037867567 | jidetechnicalco@gmail.com | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 15 | Ubani Technical Services | Isreal Ejure | 08065897533 | shalomegure2015@gmail.com | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 16 | Evercurrent Technical Company | Engr, Daniel O. Adebayo | 08065417390 | everncurrent@gmail.com | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 17 | A Honesty Tech/General Ent. | Akande Aderemi | 08028378782 |  | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 18 | Dare Kilaso Ventures | Dare Kilaso | 08095358605 | darekilasoventures@gmail.com | North West | ICE MAKING MACHINE |  |
| 19 | Elharun Construction Company | Ilyasu Abdulhameed | 8023101662 08028672143 | Iharunmusa57@gmail.com | North West | ICE MAKING MACHINE/ COLD ROOM/ REFRIGERATOR |  |
| 20 | Chris Sunny Refrigeration | Balogun Christopher S. | 08035035298 |  | North Central | ICE MAKING MACHINE/ COLD ROOM |  |
| 21 | Supreme Refrigeration Works | Isaac Kunle Oni | 08034660685 | oniisaac@gmail.com | North Central | ICE MAKING MACHINE/ COLD ROOM |  |
| 22 | Vic-Mon Technical |  | 07068284458 08055183680 |  | North Central | ICE MAKING MACHINE |  |

Enterprises for training at Lagos designated centre

| S/n | Company | Name of contact person onwer | Number of contact person | Email address of contact person | Geo-political zone | Type of business | Training session |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Perabeam Limited | Adeola Akindele | 0-8095389001 | adeola.akindele@perabeam.com | South West | ICE MAKING MACHINE | Session #2 (one trainee per company) |
| 2 | Baosam Concepts | Ajayi Babatunde Samuel | 08028765707, 08033849871 | ajayibabatundesamuel@gmail.com | South West | ICE MAKING MACHINE |  |
| 3 | A O A Technical Company | Akinniyi Olusegun | 08131518148, 08055519428 | akinniyi-olusegun9@gmail.com | South West | ICE MAKING MACHINE |  |
| 4 | Edencool Technical Works | Adeniyi Adeleke Emmanuel | 08056024699, 08034173401 | edencooltechnicalworks@gmail.com | South West | ICE MAKING MACHINE / COLD ROOM |  |
| 5 | Ade Tech | Adeoye Liadi | '08059750447 |  | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 6 | Awosco Cooling Works | Oluwalusin Olajumoke | 08038303003 | oluwalusinolajumoke@gmail.com | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 7 | Adekola Adewale Tech Engineering | Adekola Adewale | 08034301195 | adekolaadewale@gmail.com | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 8 | Odunyemi Commercial Enterprises | Moronfoye Akinwumi Odunyemi | 08037554450 |  | South West | ICE MAKING MACHINE |  |
| 9 | Folab Technical Works | Areo Afolabi Foley | '08061300169 | afolabifoley@yahoo.com | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 10 | ABIODUN TECHNICAL SERVICE | ABIODAN ADETUNJI | 08033957130 |  | South West | ICE MAKING MACHINE |  |
| 11 | Amusat Oladoke Enterprises | Alhaji Sulaiman Opeloyeru | 08072150590/ 08027270229 | opeloyerubiz@gmail.com | South West | ICE MAKING MACHINE |  |
| 12 | S. ABBEY NIGERIA COMPANY ENT. | ABIODUN BAMIDELE OLUWAGBOYEGA | 08033804994/ 08053171920/ 07055298031/ 08186777014 | duadolechmcalservices@yahoo.com | South West | ICE MAKING MACHINE/ ICE FREEZING MACHINE |  |
| 13 | Femtek Nig Enterprises | Femi Jayeoba | 07053688873 | femijayeoba61@gmail.com | South West | ICE MAKING MACHINE |  |
| 14 | Abiodun Morakinyo Nig Enterprises | T. Morankinyo | 08057976317 |  | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 15 | Morakinyo De Cool Merchant Nig Company | Morakinyo Ismaila Yusuff | 08034970478 07055323621 |  | South West | ICE MAKING MACHINE | Session #3 (one trainee per company) |
| 16 | Mofol Cool | Latifa Niyi Folorunso | 08038268706 |  | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 17 | Fash Tech Consult | Fasola Rafiu Idowu | 08026313955 | fasholaraifu@gmail.com | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 18 | Sam Goodness Technical Enterprise | Adeoti Olusegun Samuel | 08077163908 | adeotisegun14@gmail.com | South West | SERVICING |  |
| 19 | Missty Tee Tech Multiservice4s | Abdulkareem Agbolagade | 08033565482 08182932236 | adebisi406@gmail.com | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 20 | AMUDA JAMIU AFOLABI JAMOTECH VENTURE | AMUDA JAMIU | 0-8089438288/ 0-8103112121 | ogidansikiru@gmail.com | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 21 | Soltech Refrigeratiuon Works (Nigeria) | Aina Olusola | 08038176772/08099214571 |  | South West | ICE MAKING MACHINE |  |
| 22 | Das Bam and Company Ltd | Sunday Bamidele Olowookere | 0-8023424089 | dasbamcompany@gmail.com | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 23 | A K Faithful Technical Industries | Abdulkareem Yakubu | 0803478112 08055530792 | akfaithfultechnicalindustries22@gmail.com | South West | ICE MAKING MACHINE |  |
| 24 | AKAND-ALADE ALLIU TWINS TEC | AKANDE ALADE | 0-8034065253 |  | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 25 | Clem Makanjuola Nig Ent. | Clement Makanjuola | 0-8023055265 | clemmakanjuola@gmail.com | South West | ICE MAKING MACHINE |  |
| 26 | Jubson Technical Company | Mrs Rukiayat Ogundana | 08033776568 | jubrilogundana@yahoo.com | South West | ICE MAKING MACHINE |  |
| 27 | Bencool Tech Int | Benjamin Olorunda | 08038592799/09039546369 |  | South West | ICE MAKING MACHINE |  |

Enterprises for training at Port Harcourt, Rivers State training centre

| S/n | Company | Name of contact person | Number of contact person | Email of contact person | Geo-political zone | Tupe of business | Training session |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Obi Electrical Engineering | Obi Olovo | 0-8037424039 |  | South East | ICE MAKING MACHINE | Session #4 (one trainee per company) |
| 2 | Felix Cooling Technical | Felix Imumonlen Eromosele | 0-8023371730 | ozavesheade@gmail.com | South South | ICE MAKING MACHINE |  |
| 3 | Michael Fast Cool Nig | Michael Akaya | 0-7033677546 |  | South South | ICE MAKING MACHINE |  |
| 4 | Charles Oranebo Investment Nig. | Charles Ohanebo | 0-8036081729 |  | South East | ICE MAKING MACHINE |  |

Location of Training: Group III companies

The trainings will also be held for the 115 Group III enterprises at the same aforementioned three  designated Centers of Excellence as designed by the National Ozone Office (NOO) of Nigeria. The training will be held at Kano, Port Harcourt and Lagos.

Enterprises for training at Kano designated centre

| S/n | Company | Location | Geo-political zone | Type of business | Training session |
| --- | --- | --- | --- | --- | --- |
| 1 | Sholl-Sammy Associate (ENGR) Works | Kano/Kano | Norh West | ICE MAKING MACHINE/ COLD ROOM | Session #5 (one trainee per company) |
| 2 | MARTINS TECHNICAL COMPANY | ABUJA | North Central | ICE MAKING MACHINE |  |
| 3 | AUSREAL TECHNICAL CO. | ABUJA | North Central | ICE MAKING MACHINE |  |
| 4 | Johnson Kay Services | Kwara/Ilorin | North Central | ICE MAKING MACHINE/ COLD ROOM |  |
| 5 | Koseru Technical Services | Kwara/Ilorin | North Central | ICE MAKING MACHINE/ COLD ROOM |  |
| 6 | Oyetech Nig | Kwara/Ilorin | North Central | ICE MAKING MACHINE/ COLD ROOM |  |
| 7 | R & A Place | Kwara/Ilorin | North Central | ICE MAKING MACHINE/ COLD ROOM |  |
| 8 | HOLY WATER TECHNICAL ENTERPRISE | ABUJA | North Central | ICE MAKING MACHINE/ WATER COOLING MACHINE |  |
| 9 | OKOTI TECHNICAL COMPANY LTD | ABUJA | North Central | ICE MAKING MACHINE |  |
| 10 | Flamin go Cooling (NIG) enterprise | Kogi/Ajaokuta | North Central | ICE MAKING MACHINE |  |
| 11 | MACHI TECH | ABUJA | North central | ICE MAKING MACHINE |  |
| 12 | JASMOD NIG ENTERPRISES | Abuja | North central | ICE MAKING MACHINE |  |
| 13 | J. J. Johnson Engineering Enterprises | Kogi/Lokoja | North central | ICE MAKING MACHINE/ COLD ROOM |  |
| 14 | FEMOO COOL NIGERIA LTD | Abuja | North Central | ICE MAKING MACHINE/ COOLER BOX |  |
| 15 | FRANCO ELECTRICAL WORK | Abuja | North Central | ICE MAKING MACHINE |  |
| 16 | BAABAGIDA IBRAHIM ELECTRICAL | Abuja | North Central | ICE MAKING MACHINE |  |
| 17 | THEERMOCOOL COOL WORLD ENTERPRISES | Abuja | North Central | ICE MAKING MACHINE |  |
| 18 | JOHNYCOOL TECH. VENTURE | Abuja | North Central | ICE MAKING MACHINE |  |
| 19 | JODAMAF TECH. NIG. LTD | Abuja | North central | ICE MAKING MACHINE |  |
| 20 | DANY BEST TECHNICAL VENTURE | ABUJA | North Central | ICE MAKING MACHINE |  |
| 21 | JOF-TECH TECHNICAL COMPANY | Abuja | North Central | ICE MAKING MACHINE |  |
| 22 | JOHN OSIKE FABRICATION WORK | Abuja | North Central | ICE MAKING MACHINE |  |
| 23 | DE-RAY AND CO TECH | Abuja | North Central | ICE MAKING MACHINE | Session #6 (one trainee per company) |
| 24 | ALIU COOLS TECH. CO | Abuja | North Central | ICE MAKING MACHINE |  |
| 25 | ELECTRO-DATERO NIGERIA LIMITED | Abuja | North central | ICE MAKING MACHINE |  |
| 26 | OLALEYE TECHNICAL LTD | Abuja | North Central | ICE MAKING MACHINE/ COLD ROOM/PURE WATER |  |
| 27 | SHONCOOL REFRIGERATINO AIR COND. ENTERPRISES | Abuja | North Central | ICE MAKING MACHINE /COLD ROOM/FRIDGE/ AIR CONDDITIONER |  |
| 28 | COOLCITY FRIDGE TECHNICAL COMPANY | Abuja | North central | ICE MAKING MACHINE/ OVEN/ LOCAL BAKERY |  |
| 29 | USARIK ENG. NIG LTD | Abuja | North Central | ICE MAKING MACHINE |  |
| 30 | AZEMOH & AZEMOH TECH SERVICE | Abuja | North Central | ICE MAKING MACHINE |  |
| 31 | ALBARKA WAVES CONCEPT LTD | ABUJA | North central | ICE MAKING MACHINE/ COLD ROOM |  |
| 32 | EZETHEC TECHNICAL SERVICES | Abuja | North Central | ICE MAKING MACHINE |  |
| 33 | Dens and Sons Nig Ent | Kogi/Lokoja | North Central | ICE MAKING MACHINE |  |
| 34 | FRIJIM ELECTRICAL ELECTRONIC | ABUJA | North central | ICE MAKING MACHINE /COLD ROOM |  |
| 35 | EMMANCO ANHERI ENT. | Abuja | North Central | ICE MAKING MACHINE |  |
| 36 | CHAN - THE COOL ENT. | Abuja | North Central | ICE MAKING MACHINE/ COLD ROOM |  |
| 37 | CHUKS COOL TECH. COMPANY | Abuja | North Central | ICE MAKING MACHINE |  |
| 38 | KAYBETH TECHNICAL | ABUJA | North Central | ICE MAKING MACHINE |  |
| 39 | DOECCOOL TECHNICAL | Abuja | North Central | ICE MAKING MACHINE |  |
| 40 | ISIAKU MUSA ELECTRICAL WORK | Abuja | North central | ICE MAKING MACHINE |  |
| 41 | FANEX SYSTEM NIG. | ABUJA | North central | ICE MAKING MACHINE |  |
| 42 | SOLOTECH ELECT. NIG. ENT. A/C & REF. | ABUJA | North central | ICE MAKING MACHINE |  |
| 43 | Ibrahim Muazu Tech Works | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 44 | United Tech Enterprises (Babington Technical Enterprises) | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 45 | Patrick Abu Technical Company | Kano/Kano | North West | ICE MAKING MACHINE | Session #7 (one trainee per company) |
| 46 | N U Engineering Tech | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 47 | Rivers Electrical & Mechanical Company | Kano/Kano | North West | ICE MAKING MACHINE |  |
| 48 | Hamadex Technical Services | Kano/Kano | North West | ICE MAKING MACHINE |  |
| 49 | Suleiman Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 50 | OC Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 51 | BESTMAN TECHNICAL WORKS | Abuja | North West | ICE MAKING MACHINE |  |
| 52 | Taoteco Technical Works | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 53 | Aray Home Air Conditioning Clinic | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 54 | God With Us Feel Engineered Works | Kaduna/Kaduna | North West | ICE MAKING MACHINE |  |
| 55 | Tunde Technical Services | Kano/Kano | North West | ICE MAKING MACHINE |  |
| 56 | Tadlok enterprises | Kano/Kano | North west | ICE MAKING MACHINE/ COLD ROOM |  |
| 57 | Champion Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 58 | Taiye Technical Works | Kano/Kano | North west | ICE MAKING MACHINE/ COLD ROOM |  |
| 59 | Abbey Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 60 | Tajudeen Abdulsalam Tech Works | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 61 | Sam Technical Refridgelant | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 62 | Amark Technical Company | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 63 | Tunde Technical Works | Kano/Kano | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 64 | Achyman Global Link Services | Kaduna/Kaduna | North West | ICE MAKING MACHINE/ COLD ROOM |  |
| 65 | ADAMS TECH. EMERGENCY | Abuja | Noth Central | ICE MAKING MACHINE |  |

Enterprises for training at Port Harcourt, Rivers State training centre

| S/n | Company | Location | Geo-political zone | Type of business | Training session |
| --- | --- | --- | --- | --- | --- |
| 1 | N-NDU ELECTRICAL | Aba | South East | ICE MAKING MACHINE | Session #8 (one trainee per company) |
| 2 | PEE COOLING TECH. | Aba | South East | ICE MAKING MACHINE/ COLD ROOM |  |
| 3 | GODS OPINIO TECHNICAL NIG. | ONITSHA | South East | ICE MAKING MACHINE |  |
| 4 | E-PAL ENTERPRISES NIG LTD | Aba | South East | ICE MAKING MACHINE |  |
| 5 | UGOWE ENG. COMPANY | Benin | South South | ICE MAKING MACHINE/COLD ROOM/ BUILDING OF MINI COLD |  |
| 6 | GEOWHO ENINGEERING INTERNATIONAL COMPANY | Portharcourt | South South | ICE MAKING MACHINE/ CENTRAL UNIT, COLD STORE |  |
| 7 | CHRISTOLY NIG. ENTERPRISES | PORT HARCOURT | South south | ICE MAKING MACHINE |  |
| 8 | OGTECH ELBART LTD | PORT HARCOURT | South South | ICE MAKING MACHINE/ COLD ROOM |  |
| 9 | A. Z. MOMOH NIGERIA LTD | Port Harcourt | South south | INDUSTRIAL COLD ROOM, MARINE COLD ROOM, BOX TRUK COLD ROOM |  |
| 10 | OHAVIC VENTURES | PORT HARCOURT | South South | ICE MAKING MACHINE |  |
| 11 | SAROCOOL TECHNICAL SERVICES | PORT HARCOURT | South South | ICE MAKING MACHINE |  |
| 12 | NESCO TECHNICAL SERVICE CO. | PORT HARCOURT | South south | BOX TRUCK COLD ROOM, MARINE COLD ROOM, INDUSTRIAL COLD ROOM |  |
| 13 | AUSTIN LAZ & CO PLC | BENIN | South South | ICE MAKING MACHINE |  |
| 14 | DE HEROES REFRIGERANTINO CO. | PORT HARCOURT | south south | COLD ROOM/ INDUSTRIAL REFRIGERATION |  |
| 15 | ANGSONS ENTERPRISES | PORT HARCOURT | South south | ICE MAKING MACHINE/ COLD ROOM |  |
| 16 | COOLMAN TECH SERVICES | Akwa Ibom | South south | COLD ROOM |  |
| 17 | Pauli Brothers and Company | Enugu/Enugu | South East | ICE MAKING MACHINE |  |
| 18 | IFECO CONSRUCTINO CO. NIG. | Obosi/Anambra | South East | ICE MAKING MACHINE/ ICE CREAM, BOTTLE WATER, DEEP FREEZER |  |

Companies for training at Lagos designated centre

| S/n | Company | Location | Geo-political zone | Type of business | Training session |
| --- | --- | --- | --- | --- | --- |
| 1 | SamueL Technical Works | Oyo/Oyo | South West | ICE MAKING MACHINE | Session #9 (one trainee per company) |
| 2 | Jumascoi Technical Engineering Company | Oyo/Ibadan | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 3 | BEST JOHNNY TECHNICAL COMPANY | Abeokuta | South West | ICE MAKING MACHINE |  |
| 4 | AJAYI EZEKIEL | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 5 | Castrol Joe Tech. | Akure/Ondo | South West | COLD ROOM |  |
| 6 | SIKFAT COMM. ENT. | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 7 | ELECTRICAL ENG. CO. | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 8 | OLALEKANCOOL SERVICES NIG. | Lagos | South West | ICE MAKING MACHINE |  |
| 9 | AJITECH TECHNIAL SERVICES | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 10 | Oyegoke Electrical Works | Oyo/Ibadan | South West | ICE MAKING MACHINE/ CHILLERS, AIR CONDITIONERS |  |
| 11 | Nurudeen Adeojua Ice Block Making Machine | Oyo/Ibadan | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 12 | Orosun Nigeria Limited | Ogun/Ijebu Ode | South west | ICE MAKING MACHINE |  |
| 13 | OLU-ADE TECHNICAL SERVICES | ABEOKUTA OGUN STATE | South West | ICE MAKING MACHINE |  |
| 14 | Dansfocus Technical Company | Oyo/Ibadan | South West | ICE MAKING MACHINE |  |
| 15 | FAVOUR ONA VENTURE | ABEOKUTA OGUN STATE | South west | ICE MAKING MACHINE |  |
| 16 | Deekay and Sons Nigeria LTD | Lagos/Lagos | South West | Nexus refrigeration appliances and air conditioners |  |
| 17 | SUNNY OKEOWO NIGERIA ENTERPRISE | Lagos State | South west | ICE MAKING MACHINE |  |
| 18 | Moonlight Electrocooling Services | Oyo/Ibadan | South west | ICE MAKING MACHINE/ COLD ROOM |  |
| 19 | Adrosh Co Ltd | Lagos State | South West | ICE MAKING MACHINE |  |
| 20 | Hamzat Technical Services | Lagos/Lagos | South West | ICE MAKING MACHINE |  |
| 21 | Popson Technology Service Works | IBADAN | South west | ICE MAKING MACHINE |  |
| 22 | BIDBELL VENTURES | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 23 | Polade | Lagos State | South West | ICE MAKING MACHINE/ COLD-ROOM PANES, SPRAY WORK | Session #10 (one trainee per company) 10 companies from Group III + 10 KIP companies |
| 24 | DEKOOLAR NIG LTD | Papalanto/Ogun State | South west | ICE MAKING MACHINE/ COLD ROOM/ FREEZER/ OVEN |  |
| 25 | Fakeye Corporate Enterprises | Oyo/Ibadan | South West | ICE MAKING MACHINE |  |
| 26 | AjibadeTech Work | Oyo/Ibadan | South West | ICE MAKING MACHINE |  |
| 27 | Samdeb (Nig) Enterprises | Ibadan/Oyo | South west | ICE MAKING MACHINE/ CHILLERS, AIR CONDITIONERS |  |
| 28 | OLATEECH | Lagos | South west | ICE MAKING MACHINE/ COLD ROOM |  |
| 29 | Coldcare Nigeria Ltd | Lagos State | South West | commercial, industrial and residential refrigeration |  |
| 30 | OSENI TECH. ENTERPRISE | OGUN STATE | South West | ICE MAKING MACHINE |  |
| 31 | BAYOSON TECHNICAL | Lagos | South West | ICE MAKING MACHINE/ COLD ROOM |  |
| 32 | Olurotimi Olufowose NIG Ent | Oyo/Ibadan | South West | ICE MAKING MACHINE |  |
| 1 | Fouani Nig Ltd | Lagos | South West | Refrigerators, Freezers and Acs (LG, Hisense) |  |
| 2 | New Homes Distribution Africa Ltd | Lagos | South West | ACs and Frigdes (Midea and Scanfrost) |  |
| 3 | Cold Hubs Ltd | Lagos | South West | Cool rooms |  |
| 4 | Koolboks Nig. Ltd | Lagos | South West | Koolboks Freezers |  |
| 5 | SIM Nig. Ltd | Lagos | South West | Refrigerators/Freezers |  |
| 6 | JMG Ltd Abuja | Abuja | North Central | Fridges, Freezers and ACs ( TCL, AEON, Toshiba) |  |
| 7 | JNC Motors Ltd | Abuja | North Central | ACs (Gee) |  |
| 8 | Choice International Group (CIG) Motors Co. Ltd | Abuja | North Central | GAC Motors, JMC Motors and Wulling Motors |  |
| 9 | JAC Motors Ltd | Lagos | South West | JAC Motors |  |
| 10 | Innoson Vehicle Manufacturing co. ltd | Anamabra | South East | Innoson Motors |  |

8) Training

As noted in above, both Group II and Group III , as well as 10 KIP companies are to be trained. In total this amounts to 178 companies, Group II accounts for 53 enterprises, Group III accounts for 115 and KIP accounts for 10 enterprises.

The training sessions have been divided according to the least distance of the companies to the three above mentioned training centres. See below the total number of training sessions established per location.

Total number of training sessions

| Training Centre | Group II (53 companies) | Group III (115 companies) |  |
| --- | --- | --- | --- |
| Kano State | 1 | 3 | Each session lasts for three days |
| Port Harcourt | 1 | 1 |  |
| Lagos | 2 | 2 |  |
| Total | 10 sessions |  |  |

|  | Session | Location | Amount of trainees |
| --- | --- | --- | --- |
| Group II | Session #1 | Kano | 22 |
|  | Session #2 | Lagos | 14 |
|  | Session #3 | Lagos | 13 |
|  | Session #4 | Port Harcourt | 4 |
| Group III | Session #5 | Kano | 22 |
|  | Session #6 | Kano | 22 |
|  | Session #7 | Kano | 21 |
|  | Session #8 | Port Harcourt | 18 |
|  | Session #9 | Lagos | 22 |
|  | Session #10 | Lagos | 20 (10 KIP ) |

Final training

As mentioned above, a separate, final  training (one day) with 196 companies must be held in order to recall all important information that the trainees were taught. In addition, the usage and importance of keeping a logbook must be demonstrated at this training.

|  | Location | Topics | Beneficiary companies | Trainees |
| --- | --- | --- | --- | --- |
| 1st half of the training | UNIDO Office in Lagos | Equipment dissemination Logbook usage | GI, GII, GII, 15 KIP | 196 |
| 2nd half of the training | UNIDO Office Lagos | Maintenance | GI, GII, GII, 15 KIP | 196 |

- General Time Schedule

This contract shall be executed within a twelve-month period. Each training session will hold for three days each which will include both theory and practical exercises. There shall be one training for three days per group of maximum 22 persons per location as stated in the three location tables above. The successful bidder will work in cooperation with the NOO and UNIDO, training invitation letters shall be developed and sent to trainee enterprises not less than two weeks before the travel date of the start of the training sessions.  After completion of all the above mentioned trainings, a one-day training session for Group I, Group II, Group III and KIP companies (196 enterprises) shall be held in Lagos at a future date.

- Technical Requirements

Experience:

The contractor responsible for organizing logistics and administration must possess relevant experience organizing similar technical training workshops for refrigeration and air-conditioning technicians and to have prior experience of work (at least three years) with government and UN institutions. The contractor should have substantial experience in organizing workshops and provide three samples of previous work done. CVs of the proposed key personnel are to be provided. A list of minimum three similar project references is to be provided.

The contractor should also provide a list of equipment and material necessary for conducting the trainings (i.e. projector, flipcharts etc.) In addition to this, the contractor must provide UNIDO with intermediate reports after finishing the trainings at each location, as well as a final report after completion of the final training. Up until three days after completion of the trainings in Kano, UNIDO is to receive an intermediate report . After completion of the trainings in Port Harcourt, UNIDO shall receive an intermediate report up until three days after completion. The same counts for completion of trainings in Lagos and the final report.

Proposal content:

- Proposal shall include a preliminary time schedule with a proposal for executing the project. The total project duration should not exceed eight months from the date of award to the date of handover.

- Bidders may choose to provide financial proposal for the required services and related equipment for all three locations in Nigeria. Partial bids (for one or two locations only) would not be accepted.

- Language Requirements

All official communications and training sessions will be done in English. All the training materials have be prepared in English. In addition, the contractor must be able to understand Pidgin English.

- Deliverables

| Schedule | Deliverables | Payments |
| --- | --- | --- |
| Upon signature | - Signed contract; - Workplan; - A list separating the enterprises by businesses into training groups 22 people maximum; - Pre- and post- evaluation questionnaires; - Draft designs for banners, flyers, jotters, pen bags and any other training materials, which were developed in cooperation with NOO of Nigeria; - Design of certificate of participation; - Training sessions agenda for Kano, Lagos, Port Harcourt and a final session in Lagos; - Invoice. | 40% |
| Completion of the contract | - A sex segregated list of participants - Photos links and hard drive - Copies of printed training manuals and materials - Report on final evaluation for each participant - Transaction records for hotels and bus services, air tickets, including proof of payment of allowances - Copies of certificates given to each participant - Copies of media reports from prints, TV, radios etc - Social media report with links to the publications on X, Instagram, Face book and any other social media platforms - Detailed training report (four in total) with feedback from participants on training sessions including consultant’s recommendation on areas of improvement and schedule of subsequent training programs - Signed distributed list of distributed equipment to enterprise trainees - Final contract report Invoice | 60% |

- PROPOSALS

Proposals shall be quoted in USD including levies, taxes in line with the attached Technical Specifications.

- TECHNCIAL REQUIREMENTS AND SUPPLIER RESPONSIBILITY

The supplier shall consider all the details presented in these technical specifications and shall request any further information, which is considered necessary for the correct supply of the equipment (safety boots, charts, souvenirs etc.). The supplier should fill in the table with costs and relevant information.

All deviations from these technical specifications should be clearly indicated and explained in the offer. All partial and/or non-binding offers will be rejected. In close consultation with UNIDO, the Bidder will supply the following items:

- Warranty Terms

- Terms

The supplier should bring materials such as projectors and flipcharts to each training centre prior the trainings

The supplier should bring safety-boots and reflective jackets to each training centres prior the trainings and then to disseminate it among trainees.

- Language Requirements

All official communications and training sessions will be done in English. All the training materials have to be prepared in English.